# Annex 1 to the Memorandum

# 6th  Meeting of the COOMET Presidential Council

COOMET Development Program for 2003-2004

| No | Name of an event | Terms | Executors | Remarks |
| --- | --- | --- | --- | --- |
| I. Continuous improvement of COOMET infrastructure and management of work |
| 1.1 | Development of a Conception of co-operation in COOMET: Working out a draft of the Conception Refinement and approval Adoption | September 2003 November 2003 April 2004 | SC 4.1 Presidential Council COOMET Committee | Working out of supplements to this Program (during 3 month after adoption of the Conception) |
| 1.2 | Approval and implementation of the financing scheme for the COOMET cooperation arrangements | April-May 2004 | COOMET Secretariat, COOMET Committee members from Germany and Russia |  |
| 1.3 | Setting up of COOMET Structural bodies (TC and SC) | February – December 2003 | Heads of Structural bodies (SBC) COOMET Secretariat |  |
| II. Encouragement of work in some fields of cooperation |
| 2.1 | In the filed of measurement standards |  |  |  |
| 2.1.1 | Carrying out a complex of work on implementation of the Agreement on mutual recognition of national measurements standards (MRA) | 2003-2004 | Representative of COOMET to JCRB (Joint Committee on measurement standards) |  |
| 2.1.2 | Creation and keeping of a database on CMC of the NMIs in COOMET member-countries | 2003-2004 | Joint Committee on measurement standards ТC 1.1-ТC 1.11, SC 4.2 |  |
| 2.1.3 | Development and realisation of the Program of inter-laboratory comparisons and calibration of measurement standards for 2003-2004 | 2003-2004 | Joint Committee on measurement standards ТC 1.1-ТC 1.11 | Initiation of a COOMET Project on working out a Program of inter-laboratory – March 2003. |
| 2.1.4 | Development of Recommendations on organisation of comparisons and calibrations of measurement standards in the frame of COOMET projects | February 2004. | TC 1.1 | Initiation of a COOMET Project on working out the Recommendations – April 2003 |
| 2.1.5 | Translation into English of Regulations for the COOMET Joint Committee on measurement standards and the Procedure for inner review of calibration and measurement capabilities of NMIs in COOMET member-countries and capabilities submitted for interregional review by other RMO | February 2004 | COOMET Secretariat Joint Committee on measurement standards |  |
| 2.1.6 | Refinement of documents mentioned in the line 2.1.5 (based on the results of trial implementation) | September 2003 | Joint Committee on measurement standards |  |
| 2.1.7 | Development of provisions regulating work of TC of Joint Committee on measurement standards | February - September 2003 | TC 1.1- TC 1.12 | Initiation of COOMET Projects on working out relevant provisions – March 2003 |
| 2.1.8 | Development of Recommendations on implementation of the system ATA-CARNET and provisions of the CIS Agreement on tax free policy (in force since 1995). | 2003 | Joint Committee on measurement standards TC 1.1 | Initiation of COOMET Project on working out a relevant document – March 2003 |
| 2.2 | In the field of legal metrology |  |  |  |
| 2.2.1 | Development and realisation of the Work program in the field of legal metrology | 2003-2004 | TC 2 | Project 263/RU/02 (the program is expected to be completed in April 2003) |
| 2.2.2 | Organisation of an International Conference “Role of metrology in globilized market ” | 12-14 of May 2003 | TC 2 COOMET Secretariat COOMET Committee members from Germany and Russia |  |
| 2.2.3 | Working out of regulations for the TC on legal metrology and its functional units | April 2004 | TC 2, TC 2.1 - TC 2.4 | Initiation of COOMET Projects on development of relevant regulations - March 2003. |
| 2.2.4 | Analysis of the scope of projects proposed by international and regional organisations on legal metrology. Preparation of suggestion on collaboration with these organisations. | 2003 | TC 2, SC 2.1 | Initiation of COOMET Project – April 2003 |
| 2.3 | In the field of QMS and accreditation |  |  |  |
| 2.3.1 | Development of regulations concerning the work of COOMET Quality Forum and its units | April 2004 | TC 3.1, SC 3.1-SC 3.3 | Initiation of COOMET Project on development of relevant regulations - April 2003 |
| 2.3.2 | Development and implementation of the Collaboration program in the framework of COOMET Quality Forum | 2003-2004 | TC 3.1, SC 3.1 - SC 3.3 | Finishing of development of the Program – April 2003 |
| 2.3.3 | Dispatching of the new revision of Recommendations on assessment of NMI’s Quality management systems (translated into Russian) | February 2003 | TC 3.1 |  |
| 2.3.4 | Calling up for suggestions on organisational and financial aspects of establishing a regional organisation on accreditation “COOLAC” | April 2004 | Interested members TC 3.1 | According to schedule agreed |
| 2.3.5 | Arrangement of a COOMET Workshop «Philosophy of creation and implementation of Quality management systems of test and calibration laboratories according to ISO IEC 17025 | November 2003 | TC 3.1 COOMET Secretariat | Initiation of COOMET Project - March 2003 |
| 2.3.6 | Analysis of the Accreditation systems, which are currently implemented in the COOMET member countries and ways of their future development | 2003 | TC 3.1 | Initiation of COOMET Project - April 2003 |
| 2.4. | Development of projects in the field of training and information dissemination |  |  |  |
| 2.4.1 | Working out a plan of arrangements for development of co-operation in the field of personnel training | October 2003 | SC 4.3 | Initiation of relevant COOMET Project on - April 2003 |
| 2.4.2 | Working out a plan of arrangements for continuous improvement of information dissemination | October 2003 | SC 4.2 | Taking into consideration the project 251/BY/01 and item 8 of PC-5 resolutions |
| 2.4.3 | Development of regulations for TC on information dissemination and training as well as for its units | April 2004 | TC 4, SC 4.1 – SC 4.3 | Initiation of COOMET Project on development of relevant regulations - April 2003 |
| 2.4.4 | Renewal of information placed at COOMET Web-site (keeping of database on COOMET Projects and publications) | 2003-2004 (as of demand) | COOMET Secretariat, Site developer |  |
| III. Encouragement of collaboration with international, regional and national metrology organisations |
| 3.1 | Keeping of contacts with international and regional organisations, which maintain measurement standards: |  | COOMET President, Vice-president, responsible for collecting information on relevant achievements at international level |  |
|  | Collaboration with BIPM, EUROMET, APMP, SADCMET, SIM, etc. | Continually (as of demand) | Vice-president, responsible for co-ordination of COOMET activities in the field of measurement standards. Chairman of Joint Committee on measurement standards |  |
|  | Encouragement of participation of COOMET Representatives in the work of JCRB | According to the JCRB schedule agreed | Vice-president, responsible for co-ordination of COOMET activities in the field of measurement standards. (COOMET Representative to JCRB) |  |
| 3.2 | Keeping on contacts with international and regional organisations on legal metrology (OIML, WELMEC, APLMF, SADCMEL etc.) | Continually (as of demand) | COOMET Chairman Chairman of TC2 |  |
| 3.3 | Keeping on contacts with international and regional organisations on accreditation (ILAC, IAF, EA) | Continually (as of demand) | Vice-president, responsible for co-ordination of COOMET activities in the field of quality management system and accreditation |  |
| 3.4 | Development and realisation of COOMET program on co-operation with NTCMeter | 2003-2004 | Vice-president, responsible for co-ordination of COOMET activities in the field of cooperation with CIS countries | Working out за a Program – September 2003 Co-ordination of work carried out in the framework of COOMET and NTC Meter is essential because of COOMET members are 50% of all CIS organisations |
| 3.5 | Creating and keeping on of the contacts with national metrological organisations interested in cooperation with COOMET (Yugoslavia, Albania, Mongolia, Uzbekistan, Georgia, Armenia, etc.) | Continually | COOMET President COOMET Secretariat |  |