TC 2 Work Program for 2011 – 2012

| point | Project ID |  | Project name | Coordinator |  | Participants | Scheduled starting date |  |  | Remarks |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Chairperson TC2 Correspondence with OIML, RMOs and NMIs |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Topic |  |  | Analysis of possible fields of cooperation with OIML and regional organizations on legal metrology. Formulation of suggestions on joint work with them |  |  |  | 2011-2013 |  |  |  |  |  |
| 2.0.1 |  |  | Analysis of developments and possible cooperation in OIML, RMO's and NMI's and suggestion of joint work | O.Kuhn (LMET, Germany) |  |  | 2008 |  | General Task of Chair TC2 |  |  |  |
| 2.0.2 |  |  | Preparation a questionnaire among the COOMET Members for building up a list of experts in legal metrology | O.Kuhn (LMET, Germany) |  |  | 2009 |  | Finished |  |  |  |
| 2.0.3 |  |  | Extend the List of OIML- and WELMEC-Contact persons to its subcommittees | O.Kuhn (LMET, Germany) |  |  | 2010 |  | In progress |  |  |  |
| 2.0.4 |  |  | To collect and process information for the TC2 section of the new COOMET web portal | Secretary of Chair TC2 |  |  | 2010 |  | In progress |  |  |  |
| 2.0.5 |  |  | Holding workshops on legal metrology | Chair TC2 and TC4 |  |  | 2011 |  | 2011: 7-8.09.2011, Yerevan, Armenia (finished) |  |  |  |
| SC 2.1 Harmonization of Regulations and Norms in Legal Metrology |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Topic |  |  | Checking documents and recommendations of OIML and other RLMO’s for adaption or acceptance in COOMET |  |  |  | 2011-2013 |  |  |  |  |  |
| 2.1.1 | 424/BY/08 |  | Translation of new project of VIM | N. Zhagora (BelGIM, Belarus) |  | Belarus, Russia, Ukraine | 2008 |  | Finished (2011) |  |  |  |
| 2.1.2 | 427/BY/08 |  | Analysis of requirements in the field of legal metrology including examples of application of these requirements to measuring instruments | N. Zhagora (BelGIM, Belarus) |  | Belarus, Russia, Ukraine | 2008 |  | In progress |  |  |  |
| 2.1.3 | New 2009 |  | Translation of international vocabulary of legal metrology (VIML) | VNIIMS |  | Russia, Belarus | 2009 |  | under registration |  |  |  |
| 2.1.4 | New 2010 |  | To check out uniformity of erification\calibration certificates issued in COOMET member countries and come up with a suggestion on unification, if required (initiator is Ukraine) | NNC “IM”, Ukraine |  | Belarus, Russia, Ukraine | 2010 |  | under registration |  |  |  |
| 2.1.5 | New 2010 |  | Analysis of OIML D16 ”Principles of assurance of metrological control” | O. Kühn (LMET, Germany) |  |  | 2011 |  | To present at the Seminar (2011) |  |  |  |
| 2.1.6 | New 2011 |  | Create a database for interested and accepted rules, guides, recommendations and standards in the field of legal metrology between COOMET member-countries and other regional legal metrology organizations | O. Kühn (LMET, Germany) |  |  | 2011 |  | In progress It will be realized by putting corresponding links on the COOMET web-portal (TC2 page) |  |  |  |
| 2.1.7 | New 523/BY/11 |  | Development of a procedure for attributing technical devices to measuring instruments | M. Shabanov (BelGIM, Belarus) |  | Belarus, Russia, Ukraine, Kazhastan, Moldova, Armenia, Uzbekistan | 2011 |  | In progress To present at the TC 2 meeting (2011) |  |  |  |
| SC 2.2 Technologies of Measuring Devices and Systems in Legal Metrology |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Topic |  |  | Development of metrological control procedures for measuring instruments and measuring systems with new technologies (i.e. software, data processing, device communication) |  |  |  | 2011-2013 |  |  |  |  |  |
| 2.2.1 | 425/BY/08 |  | Development of a template of test procedure for software of measuring instruments | M. Shabanov (BelGIM, Belarus) |  | Belarus, Russia, Ukraine | 2008 |  |  | In progress |  |  |
| 2.2.2 | 437/BY/08 |  | Development of a program for generating 'reference' data sets for the purpose of software testing | M. Shabanov (BelGIM, Belarus) |  | Belarus, Russia, Ukraine | 2008 |  |  | Suspended |  |  |
| 2.2.3 | New 2010 |  | Analysis of new technologies for measuring instruments | O.Kühn (LMET, Germany) |  | Germany | 2010 |  |  | The presentation was given at the ТС 2 meeting (2010) |  |  |
| SC 2.3 Competence and Assessment of Bodies in Legal Metrology |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Topic |  |  | Development of criteria for assessment of testing laboratories working in the field of type approval, verification laboratories and other parties with the purpose of mutual recognition of the results of their work |  |  |  | 2011-2013 |  |  |  |  |  |
| 2.3.1 |  | 442/UA/08 | Analysis of criteria of technical competence used for assessment of verification laboratories | O. Maletskaya (NNC “IM”, Ukraine) |  | Ukraine, Belarus, Russia | 2008 |  |  | Taking into consideration ISO 10012, ISO 17025 Finished (presentation was made at the TC 2 meeting (2010) |  |  |
| 2.3.2 |  | 426/BY/08 | Development of recommendation regarding realization of interlaboratory comparisons (PT schemes) for verification laboratories for assessing their technical competence | M. Shabanov (BelGIM, Belarus) |  | Belarus, Ukraine, Russia | 2008 |  |  | In progress |  |  |
| 2.3.3 |  | 491/UA/10 | Development of COOMET rrecommendation "General requirements to the competence of verification laboratories" | O. Maletskaya (NNC “IM”, Ukraine) |  | Belarus, Ukraine, Russia | 2010 |  |  | In progress |  |  |
| 2.3.4 |  | New 2010 | Requirements for the testing laboratories involved in type approval testing | M. Shabanov (BelGIM, Belarus) |  | Belarus, Ukraine, Russia | 2009 |  |  | Suspended (Considering OIML D30) |  |  |
| 2.3.5 |  | New 2010 | To work out criteria for evaluating longterm performance of verification labs (by scores, etc.) | O. Maletskaya (NNC “IM”, Ukraine) |  | Ukraine | 2010 |  |  | Objectives of the project should be explained |  |  |
| SC 2.4 Legal Metrology Control |  |  |  |  |  |  |  |  |  |  |  |  |
| Development Topic |  |  | Development of interstate collaboration and mutual acceptance on legal metrological control of prepackages and measuring instruments |  |  |  | 2011-2013 |  |  |  |  |  |
| 2.4.1 | 441/RU/08 |  | Development of template of bilateral agreement on recognition of national prepackages control mark |  | R. Genkina (VNllMS, Russia) | Belarus, Russia, Ukraine |  | 2008 |  |  | Continued (draft document is available) |  |
| 2.4.2 | - |  | Workshop "Issues of prepackaged goods control" |  | PTB (Germany) VMT (Lithuania) | Azerbaijan, Armenia, Belarus, Bulgaria, Georgia, Kazakhstan, Kyrgyzstan, Lithuania, Moldova, Russia, Ukraine |  | 2008 |  |  | Finished |  |
| 2.4.3 | - |  | Analysis and Conception for Market Surveillance and proposals for establishment of an special working group |  | Proposed for discussion by O. Kühn (LMET, Germany) |  |  | 2010 |  |  | Suspended as a result of discussion at the ТС 2 meeting (2010) |  |
| 2.4.4 | - |  | Planning the participation on WELMEC-Seminars on conformity assessment and market surveillance of MID-lnstruments |  | O. Kühn (LMET, Germany) | Germany |  | 2010 |  |  | Finished |  |
| 2.4.5 | New 2010 |  | Informing on seminar “Conformity to type (CTT)” |  | O. Kühn (LMET, Germany) | interested members |  | 2011 |  |  | In progress |  |
| 2.4.6 | New 533/BY/11 |  | Development of a recommendation for determining amount of prepackage filling with the purpose to make a decision whether this prepackage is a misleading one |  | N. Lyakhova, (BelGIM, Belarus) | Belarus, Armenia, Azerbaijan, Russia, Uzbekistan and SC2.4 Members |  | 2011 |  |  | In progress The presentation was given at the ТС 2 meeting (2011) |  |