Prof. Dr.-Ing. K.-D. Sommer	                                          Annex 1, Draft

COOMET Vice President

Braunschweig, 2012-06-27

Project:

Elaboration of a concept for a

European-Asian Metrology Research Venture

under the auspices of COOMET

Draft Roadmap for Implementing a European-Asian Metrology Research Venture (EAMRV)

Phase 1:	State-of-art analysis and identification of national and regional needs for joint research of COOMET members in metrology

  - Elaborating questionnaires to

- underpin the national state-of-art analyses,

with the view to the emerging great challenges to humanity,

- identifying of national and joint research needs,

- laying the foundations for capacity building in metrology, and

- evaluating the attainable impact in society and economy.

Resp.:	Vice President K.-D. Sommer together with the COOMET Secretary
Date:	June 2011

1.2	Replying the above questionnaires:

Analysis of the national state of art in metrology (regarding excellence in metrological research as well as capacity building) and identification of both, national and joint research needs.

Resp:	NMIs of COOMET member states 
Date:	March 2012

1.3	Evaluating and summarizing the responded questionnaires (national state-of-art analyses and identified joint research needs with the aim to develop aCOOMET Research Report (CRR)

Resp.:	COOMET Presidential Council (PC)
Date:	March 2013

1.4	Presenting the CRR to the COOMET Committee Meeting 2013

Resp.:	PC	June 2013
Date:	April 2011

Phase 2:	Project development

2.1	Appointment of a COOMET Research Coordinating Committee (RCC)

Resp.:	COOMET Presidential Council Meeting 2012
Date:	October 2012

2.2	Developing the draft contractual foundations of a European-Asian Metrology Research Venture (EAMRV)

containing at least the following items:

    - Definition of the focal themes and aims

    - Describing the social and economic impact endeavoured

    - Definition of the structure of the programme

    - Suggestion of a financial and a time frame

    - Definition of eligible and other participants as well as of possible promoters and supporters

    - Definition of a steering committee

    - Drafting of all rules necessary, the bylaws and articles.

Resp.:	RCC
Date:	September2013

2.3	Commissioning of the COOMET-TCs to elaborate roadmaps describing the future development of metrology and measurement

Based on the existing Metrology Roadmaps of EURAMET, the COOMET TCs shall be requested to check the actuality and applicability of these roadmaps and, where necessary, to develop new or advanced ones.

Resp.: COOMET PC 2012

Date of commissioning:  October 2012

Date of finalizing the roadmaps: September 2013

2.3	European-Asian Metrology Research Conference
Participants: NMIs of COOMET member states, MGS, relevant research institutes and scientific societies of the COOMET member states, politicians, stakeholders, decision makers, BIPM, EURAMET, APMP, NCSLI etc.

Aims of the conference:

    - Awareness building for the importance of metrology for the successful mastering of the great challenges to humanity

    - Making clear the huge impact of metrology in economy and society

Organisation: RCC, COOMET Secretary and NMI of hosting country

Program Committee: RCC &International steering committee

Date:	Spring/Summer  2013
(in connection with COOMET Committee Meeting 2013?)

2.4	National programme discussions and preparations (starting in spring 2013)
a) National stakeholders talks and conferences
b) National political talks (lobbying)
    (Target groups: politicians, members of parliament, ministries etc.)

Aim of the stakeholder and political talks: Achieving willingness for financing the EAMRV

Resp.:	NMIs of COOMET member states
Date of finalization: September 2013

Phase 3:	Implementing and launching the EAMRV

3.1	Contracting the EAMRV and approval of the bylaws

Resp.:	NMIs of the COOMET member states
Date:	December 2013

3.2	Institution of the contracted structure with COOMET as the project coordinator and programme host

Resp.:	COOMET (RCC)
Date:	April 2014

3.3	First invitation of tenders (first call)

Resp.:	COOMET (RCC)
Date:	September 2014