EIGHTH MEETING

OF COOMET EXPERTS ON REFERENCE MATERIALS

## MINUTES

VILNIUS

26-27 NOVEMBER 2002

PARTICIPANTS:

Republic of Belarus

Valery Makarevich                          Representative of COOMET TC 1.12 “CRMs”

Project Coordinator,

Head of Radiation Metrology Research Department

BelGIM, Minsk.

Bulgaria

Marina Georgieva                            Project Coordinator, Director of Complex Testing and

Calibration Centre “LOVICO”

Pavlikeny.

Lithuania

Algidas Galdikas                             Deputy Director of Semiconductor Physics Institute

Mudis Shalkauskas                         TC-16 “Chemical Analysis”

Marian Grigorovich                       Lithuanian Chemist Society

Pyatros Serapinas                           Institute of Theoretical Physics and Astronomy

Vilnius

R. of Moldova

Adelaida Andriesh                         Deputy Head of Chief Metrology Board, “Moldova-

Standart” Department

Kishinev

Russia

Vladislav Leonov                         Chairman of COOMET TC 1.12 “CRMs”, Professor

Director of the Urals Research Institute for Metrology

(UNIIM), Vice-President of the Russian Academy of

Metrology

Yekaterunburg

Igor Dobrovinsky                        Project Coordinator, Deputy Director of UNIIM, Head 
                                                                of State Service of Reference Materials (GSSO)

Department, UNIIM

Yekaterinburg

Emilia Burykina                          Secretariat of the Chairman of COOMET TC 1.12

“CRMs”, Senior Researcher of GSSO UNIIM

Yekateruinburg

Valery Stepanovskikh                 Project Coordinator, Deputy Director of Closed Joint

Stock Company “Institute of Reference Materials”

Yekaterinburg

Slovakia

Anna Matiasova                            Quality Manager of Chemistry Centre, Slovak

Metrological Institute, Member of Slovak Commission

for CRMs

Bratislava

Ukraine

Stanislav Senotrusov                    Project Coordinator

Director of Bureau for Reference Materials (BSO Ltd.)

CHAIRMAN:

Vladislav Leonov                        Chairman of COOMET TC 1.12 “CRMs”

HEADS OF DELEGATIONS:

Republic of Belarus:

Head of Radiation Metrology Research Department              - Valery Makarevich

BelGIM

Bulgaria:

Project Coordinator, Director of Testing and                          - Marina Georgieva

Calibration Centre “LOVICO”

Pavlikeny

Lithuania:

Deputy Director of Semiconductor Physics                             - Algidas Galdikas

Republic of Moldova:

Deputy Head of Chief Metrology Board,                                 - Adelaida Andriesh

“Moldova-Standart” Department

Russia:

Director of the Urals Research Institute                                   - Vladislav Leonov

for Metrology,

Vice-president of the Russian Academy

of Metrology

Slovakia:

Quality Manager of Chemistry Centre,                                     - Anna Matiasova

Slovak Metrological Institute,

Member of Slovak Commission for CRMs

Ukraine:

Director of Bureau for Reference Materials                              - Stanislav Senotrusov

RESULTS OF WORK AND ADOPTED RESOLUTIONS

Agenda item 1:

Mr. O. Staugaitis, Director of Lithuanian Metrology Department welcomed the participants and opened the meeting.

He wished the participants of the meeting successful work and gave some practical information. After having been discussed the agenda was adopted (annex 1).

Agenda item 2:

Heads of delegations identified themselves and the members of their delegations.

Agenda item 3:

Participants reported on the current certified reference materials activities in Belarus, Bulgaria, Lithuania, Moldova, Russia, Slovakia and Ukraine. Written activity reports were submitted by Belarus, Bulgaria and Russia (annexes 3.1, 3.2 and 3.3 respectively). Representatives of Lithuania, Moldova and Slovakia informed the participants that they will submit the information on CRM activity in their respective countries in writing to the Secretariat of TC 1.12 “CRMs” in December 2002. Besides, Mrs. A. Matiasova informed the participants that in the 1st half of 2003 the e-version of the catalogue of CRMs approved in Slovakia (both national and foreign CRMs) will be circulated together with a price-list.

Agenda item 4:

Prof. V. Leonov spoke within the agenda item. In his presentation he reported on the main results of the 12th meeting of COOMET Committee (Cuba, Havana, May 2002) and on the priority tasks of cooperation on CRM problem in connection with the decisions taken at the Committee meeting (annex 4). Prof. V. Leonov informed the meeting on the appointment of the Representatives in TC 1.12 “CRMs” from the countries in accordance with the information provided by COOMET Secretariat (annex 4.1)

The following decision was taken:

- To take the information into account.

- To take into consideration and follow the decisions taken at the 12th meeting of

COOMET Committee in  cooperation on CRM problem.

Agenda item 5:

The current works outlined by Project Coordinators were discussed.

5.1. Information of COOMET TC 1.12 “CRMs” Secretariat on the progress of the projects  on “Certified Reference Materials” problem.

Mrs. E. Burykina presented the information of COOMET TC 1.12 “CRMs” Secretariat concerning the progress of the projects on “CRM” problem (annex 5.1).

The decision was taken as follows:

1.To take the information into account.

2. To take the information given by Mr. V. Makarevich that the authors – Coordinators

of projects 188/BY/99 and 189/BY/99 (the author: R. of Belarus) suggested that the projects should be deleted from the COOMET Working Programme.

3.To take into account the information of Mrs. M. Georgieva that the projects 198-202/BG/99 (the author: Bulgaria) will be finalized, the authors will present the reports and documentation on the developed CRMs in May 2003.

5.2. Discussing the progress of current works on the projects.

The progress of works on the projects was discussed with account for the information delivered by the Project Coordinators.

5.2.1. Project 186/RU/99 “Development of the Programme of joint CRM development within

COOMET”

Mr. I. Dobrovinsky spoke on the issue, presented the updated Programme (as of November 2002) and gave the information on the progress made in the frameworks of the Programme.

The decision was taken as follows:

1.To consider the Programme (as of November 2002) to be agreed (annex 5.2.1).

2.To find it expedient to retain in the Programme the projects already in progress (the forms of Proposed or Agreed projects are prepared).

3.To find it expedient to devide the Programme into two sections: the first section will include the projects already started  (the forms of Proposed and Agreed projects are prepared), the second section will include the projects proposed for initial consideration; to enter the information on the contact person in the column indicating the organization - proposer of the project.

4.To take into consideration that Slovakia will inform the Project Coordinator on the possibility  of its organizations to participate in certification analyses in the 1st quarter 2003.

5. To request the Secretariat of COOMET TC1.12 “CRMs” to introduce changes into the Programme taking into account the results of the discussion and proposals of Kazakhstan submitted to the meeting.

6. To request the COOMET Secretariat to place the agreed Programme (as of January 2003) at the COOMET web-site.

7. To request the representatives of COOMET member-countries to stir up the work on participation of COOMET producers in the Programme in their respective countries and to submit additional proposals on the Programme to the Secretariat of the Chairman of COOMET TC 1.12 “CRMs”  as they appear.

8. To request the Project Coordinator to present the updated version of the Programme to the next COOMET meeting on CRMs.

5.2.2. Projects 182/BG/99 “Development of CRMs for composition of drinks produced

of  distillate (3 types)”,

183/BG/99 “Development of CRMs for composition of ethyl alcohol (3 types)”,

184/BG/99”Development of CRMs  for composition of tartaric acid (1type)”

Mrs. M. Georgieva spoke on the issue, reported on the changes made in the projects and presented Technical Assignments for CRM development and informational proposals on the projects (annex 5.2.2).

The decision was taken as follows:

1. To take the information on the progress of works on the projects into account.

2. To include the projects in the Programme of Joint CRM Development within

COOMET (project 186).

3. To take into account that the author presented informational proposals to invite the participants of interlaboratory analyses (ILA), agreed Technical Assignments for CRM development with modifications in p.6 concerning the dates of carrying out the works (annex 5.2.2).

4.To take into account that Belarus, Lithuania, Moldova, Russia, Slovakia and Ukraine expressed their principal consent to participate on the projects.

5. To request the representatives of COOMET member-countries in TC 1.12 “CRMs” to address the experts of their respective countries with a view to decide on the possibility of their participation in ILA and to inform the Project Coordinator and the Chairman of TC 1.12 “CRMs” on the decision taken and the amount of RM material needed for analyses by 15 January 2003.

6. To request the Project Coordinator to re-draft the forms of Agreed  Projects, to agree upon them with COOMET Committee Member from Bulgaria and forward them to COOMET Secretariat and to the Chairman of TC 1.12 “CRMs” within a month.

5.2.3. Project 236/BY/01 “Development of CRMs for specific activity of radio nuclides

cesium-137, potassium-40 and strontium-90 in rape”.

Mr. V. Makarevich spoke on the issue, reported on the progress of works on the project and informed the participants, that the project has been transferred from “Proposed” to “Agreed” and is close to completion.

The decision was taken as follows:

- To take the information into account.

- To take into account that the Project Coordinator will send the Report on scientific-

and- technical work as soon as it is prepared and the documents for 2 types of RMs after their approval as certified reference materials of Belarus to Representatives of COOMET member-countries in TC 1.12 “CRMs” and to the Chairman of TC 1.12 to prepare conclusions on the possibility of the recognition of the developed CRMs as COOMET CRMs.

Projects 237/RU/01 “Development of CRMs for composition of gold-bearing rock, complex

ore and dunite”,

238/RU/o1”Development of CRMs for composition and properties of coal”

Mr. I. Dobrovinsky spoke on the issue and reported on the progress of works on the projects attracting the participants’ attention to the fact that the works on the development of CRMs within the projects are at the different stages; he also noted that it is planned to transfer the projects from “Proposed” to “Agreed”.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To request the Representatives of Republic of Belarus and Kyrgyz Republic in TC 1.12 “CRMs” to contact organizations among which the samples of RM material for composition of complex ore within the project 237/RU/01 were distributed, to accelerate the presentation of certification results to the Chairman of TC 1.12 “CRMs”.

3.To take into account that in the framework of the project 237/RU/01 RM material for composition and properties of coal has been prepared and the samples will be distributed among the participants of work for certification analyses in the 1st half of 2003.

4.To request the Project Coordinator to prepare the forms of Agreed projects 237/RU/01 and 238/RU/01 and send them to COOMET Secretariat and to the Chairman of TC 1.12 “CRMs” for submitting to Committee Members and including the given projects in the COOMET Working Programme.

5.2.5. Projects 239/RU/01 “Development of CRMs for composition of gold-

bearing ore “,

240/RU/01 “Development of CRMs for composition of ion solutions of gold,

silver, platinum and palladium”

Mr. I. Dobrovinsky spoke on the issue, reported on the progress of works on the projects and drew up the participants attention to the fact that the works on the projects are at the different stages and that both projects are transferred from “Proposed” to “Agreed”.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To take into account that the beginning of works on the project 239/RU/01 is

postponed to 2003 (2-3 quart.).

5.2.6. Project 241/RU/01 “Development of CRMs for composition of copper (2 types)”

Mr. I. Dobrovinsky spoke on the issue, reported on the progress of works on the project and informed the participants that the project is transferred from “Proposed” to “Agreed” and is closed to completion.

The decision was taken as follows:

1.To take the information on the progress of works on the project into account.

2.To request the Representatives of R. of Belarus and Bulgaria in TC 1.12 “CRMs” to contact their organizations among which the samples of RM material were distributed  to accelerate the presentation of certification results to the Chairman of TC 1.12 “CRMs” by the end of 2002.

- To take into account that the Project Coordinator will send the Report on scientific-

and- technical work as soon as it is prepared and the documents for RMs after their approval as certified reference materials of Russia to Representatives of COOMET member-countries in TC 1.12 “CRMs” to prepare conclusions on the possibility of the recognition of the developed CRMs as COOMET CRMs.

5.2.7. Projects 242/RU/01 “Development of CRMs for composition of carbon and alloyed

steels”

243/RU/01 “Development of CRMs for composition of carbon and alloyed

steels”

244/RU/01 “Development of CRMs for composition of alloyed steels”

Mr .V.Stepanovskikh  spoke on the issue, reported on the progress of works on the projects and informed the participants that it is planned to transfer the projects from “Proposed to “Agreed” and they are close to completion.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To take into account that in the project 242 the CRM index was modified  to RG24 – RG 31 according to CRM registration rules in Russia.

3. To take into account that  RM material to carry out ILA in the frameworks of the projects 242/RU/01, 243/RU/01 and 244/RU/01 was given to the Representative of Bulgaria during the meeting.

4.To request the Representatives of R. of Belarus and Bulgaria in TC 1.12 “CRMs” to contact their organizations among which the samples of RM material were distributed  to accelerate the presentation of certification results to the Chairman of TC 1.12 “CRMs” for R. of Belarus by the end of 2002, for Bulgaria by 30 March 2003.

5.To request the Project Coordinator to prepare the forms of Agreed projects and to send them to COOMET Secretariat and to the Chairman of TC 1.12 “CRMs” for submitting to Committee Members and including the given projects in the COOMET Working Programme.

5.2.8.Projects 245/RU/01“Development of CRMs of flash point in a open crucible - TOT set”

246/RU/01”Development of CRMs of flash point in a closed crucible – TZT set”

247/RU/01”Development of CRMs of sulphur content in petroleum products”

Mr. I. Dobrovinsky spoke on the issue, reported on the progress of works on the project and informed the participants that it is planned to transfer the projects from “Proposed” to “Agreed” and they are close to completion.  RM material and certification programme on the projects 245/RU/01, 246/RU/01 and 247/RU/01 are prepared for distribution for ILA.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To take into account that the question of  RM material transportation for ILA in the frameworks of the projects 245/RU/01, 246/RU/01 and 247/RU/01is currently being settled.

3.Taking into account the specific character of RM material being developed in the framework of the projects, to request the national bodies of ILA participating countries to facilitate the settlement of RM sending through the national representations of their countries in Moscow.

4.To take into account that the Project Coordinator prepared the forms of Agreed projects and will forward them to COOMET Secretariat and to the Chairman of TC 1.12 “CRMs” for submitting to Committee members and including the given projects in the COOMET Working Programme.

5.2.9. Projects 249/KZ/01”Development of CRMs for composition of gas conduit dust in the

production of Pb and Zn”,

250/KZ/01”Development of CRMs for composition of shaft melting furnace

dust  in the production of Cu”

Mrs. E. Burykina spoke on the issue, reported on the progress of works and informed the participants that the projects are transferred from “Proposed” to “Agreed” and are close to completion.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To request the representatives of Kyrgyz Republic in TC 1.12 “CRMs” to contact the organizations of Kyrgyz Republic among which the samples of RM material were distributed  to accelerate the presentation of certification results to the author and to the Representative of R. of Kazakhstan in TC 1.12.

3.To take into account that the Project Coordinator will send the Report on scientific-

and- technical work as soon as it is prepared and the documents for RMs after their approval as certified reference materials of R of Kazakhstan to the Representatives of COOMET member-countries in TC 1.12 “CRMs” and to the Chairman of TC 1.12 to prepare conclusions on the possibility of the recognition of the developed CRMs as COOMET CRMs.

5.2.10. Projects 252/UA/02”Development of CRMs for composition of carbon steels “

253/UA/02”Development of CRMs for composition of carbon and alloyed

steels”

Mr. S. Senotrusov spoke on the issue and reported on the progress of work on the projects.

The decision was taken as follows:

1.To take the information on the progress of works on the projects into account.

2.To request the Project Coordinator to prepare the forms of Agreed projects and to send them to COOMET Secretariat and to the Chairman of TC 1.12 “CRMs” for submitting to Committee Members and including the given projects in the COOMET Working Programme.

5.3. Revision of COOMET Methodical Recommendation R/RM/8-98 “Drawing up

documents accompanying RMs developed within COOMET”.

Mrs. E. Burykina spoke on the issue and reported on the stages of development and the main contents of the document.

The decision was taken as follows:

1.To consider the presented draft of the revision of COOMET R/RM/8-98 “Drawing up

documents accompanying RMs developed within COOMET” to be agreed (annex 5.3)

2.To agree that COOMET deals with RMs falling into the category of “certified reference materials” and therefore in translating the texts into English to use the term “CRM”.

3.To request the Secretariat to introduce changes in the registration number concerning the year of  the agreement of the revised version and to place R/RM/8-2002 at COOMET web-site.

4.To request all participants when developing CRMs within COOMET to draw up documents for CRMs in compliance with the agreed document.

Agenda item 6: Information on the progress of the Register of COOMET Certified

Reference Materials and on COOMET CRM data bank.

Mrs. E. Burykina informed the participants on the progress of the Register of CRMs developed within COOMET and on the development of the software for running  the data bank of COOMET CRMs and presented output forms of the data bank documents for data input and search in the data bank of COOMET CRMs when the bank is in operation (annex 6 in 30 pages).

The decision was taken as follows:

- To take the information into account.

- To approve the work done by UNIIM on setting up COOMET CRM data bank.

### Agenda item 7: “Information on CRM activity within international organizations (ISO/

REMCO, OIML, TC 3/SC 3, COMAR, CIS).

Mr. I. Dobrovinsky presented the information on CRM activity within the above

mentioned international organizations. The summaries of his presentations are attached:

ISO/REMCO – annex 7.1;

OIML             - annex 7.2;

COMAR        - annex 7.3;

CIS                - annex 7.4.

The decision was taken as follows:

- To take the information into account.

Agenda item 8: “Proposals on the new projects”

The decision was taken as follows:

- To take into account that proposals on new projects from the countries will be

forwarded to the Secretariat of TC 1.12 “CRMs” in the 1st quarter 2003.

Agenda item 9: “Any other business”

9.1 Organization of CRM international comparisons within COOMET

The decision was taken as follows:

1.To find it expedient to propose a new project “Development of methodical recommendations for the organization of CRM comparisons within COOMET”, to request Russia to take over the authorship of this project.

9.2. Specialists’ skill upgrading in the field of CRM development and use.

Dr. I. Dobrovinsky pointed out the importance of the problem related to the education  and training of specialists in metrology, including training of young specialists, organization of probations for leading scientists and specialists. He informed the participants that in UNIIM on the basis of educational center “Metron” the probation of specialists with a view of their skill upgrading in speciality  “Development , issue and use of CRMs” was scheduled and invited everyone who wishes to attend the probation notifying in advance the organizers  (annex 9.1 – invitation and programme of education)

The decision was taken as follows:

1.To take the information into account.

2.To request the Representatives of the countries in TC 1.12 “CRMs” to facilitate the organization of specialists’ education with a view of their skill upgrading.

Agenda item 10: Date and venue of the next meeting

The date and venue of the next meeting will be agreed upon by correspondence.

Agenda item 11: Closure of the meeting

In his closing word Mr. V. Leonov thanked the participants of the meeting for their active work, the hosts and COOMET Secretariat for organizing the meeting and making it a success and expressed the hope that the works, started in concert, will have a good continuation.