|  | ###### СООМЕТ-21/05.1 (1) |
| --- | --- |

###### COOMET DEVELOPMENT PROGRAMME FOR 2008-2010

| No. | Name of event | Terms | Executors | Remarks |
| --- | --- | --- | --- | --- |
| 1 Improvement of COOMET infrastructure and activity arrangement |  |  |  |  |
| 1.1 | Realisation of COOMET Conception of Cooperation: | Realisation time is in accordance with the Action Plan on the implementation of the Conception | Participants of cooperation in COOMET |  |
| 1.2 | Organisation of work on the implementation of the Decisions of the 23rd CGPM in connection with the possible redefinition of the main SI units | 2008 – 2010 | COOMET President, COOMET Committee Members | Within a separate plan of actions |
| 1.3 | Organisation of work on prospective planning and realisation of COOMET regional projects | 2008 – 2010 | President’s Council, COOMET Secretariat | COOMET Project 492/DE/10 was opened. The issue was discussed at the 19th and 20th meeting of COOMET Committee and the 15th meeting of COOMET President’s Council. TC 5 “Joint Research in Metrology” was established as new structural body of COOMET. COOMET Vice-Presidents K.-D. Sommer and V. Krutikov and Head of COOMET Secretariat P. Neyezhmakov formed a Working Group for developing questionnaires to determine the needs of COOMET NMIs |
| 1.4 | Realisation of the Protocol of Cooperation between COOMET and EASC in the area of metrology |  |  |  |
|  | - Consideration of the main fields of cooperation and the plan of practical events for 2008-2010 | 2008 | COOMET President, COOMET Committee Members |  |
|  | - Development of a programme of interaction between COOMET and EASC for consideration at the 18th COOMET Committee Meeting | 2008 | COOMET Secretariat, EASC Secretariat (as agreed) |  |
| 1.5 | Notification about changes in COOMET Structural Bodies (TCs and SCs) | When necessary | Chairpersons of CSB, COOMET Secretariat | COOMET Secretariat distributes the information, as it becomes available, on the changes in the memberships of the structural bodies of COOMET to COOMET Committee Members and National Secretariats |
| 1.6 | Activity on the establishment of COOMET National Secretariats in Member Countries | 2008 – 2009 | Interested COOMET Committee Members, COOMET Secretariat | 17 member countries have National Secretariats. There is no National Secretariat in Romania |
| 2 Activity in some fields of cooperation |  |  |  |  |
| 2.1 | In the area of measurement standards |  |  |  |
| 2.1.1 | Arrangements on the signing of the Agreement on Mutual Recognition (CIPM MRA) by Azerbaijan, Armenia, Georgia, Kyrgyzstan and Uzbekistan | 2008 – 2010 | Committee Members from Azerbaijan, Armenia, Georgia, Kyrgyzstan and Uzbekistan | Georgia signed the CIPM MRA on 17/06/2008. In 2008 a workshop on preparing the metrology institutes of the region to their participation in the CIPM MRA was held in Astana, Kazakhstan. In 2009, at the request of COOMET Vice-President V. Krutikov, BIPM Director A. Wallard sent a letter to heads of metrology institutions of Azerbaijan, Armenia, Kyrgyzstan and Uzbekistan with a proposal to accede to the CIPM MRA |
| 2.1.2 | Activity on the realization of the CIPM MRA | 2008 – 2010 | COOMET Representative in JCRB, Joint Committee on Measurement Standards (JCMS), TC 1.1 – TC 1.12 | COOMET representatives participate in the meetings of JCRB |
| 2.1.3 | Preparation of СМС, their analysis in COOMET and submission for an interregional review | 2008 – 2010 | Committee Members from Belarus, Kazakhstan, Moldova, Russia, Ukraine, JCMS, TC 1.1 – TC 1.12, Committee Members from Azerbaijan, Armenia, Georgia, Kyrgyzstan and Uzbekistan after the signing of the CIPM MRA | The work is performed as CMCs appear. It is suggested that CMC online review pages should be developed |
| 2.1.4 | Maintenance of the COOMET database on CMC and comparisons of measurement standards of NMIs of COOMET Member Countries | 2008 – 2010 | JCMS, TC 1.1 – TC 1.12, SC 4.2 | In progress |
| 2.1.5 | Development, updating and implementation of the Programme of Mutual Development of Reference Materials within COOMET | On continuous basis within Project 186/RU/99 | TC 1.12 | Revised Programme as of 01.01.2011 was posted on COOMET web-portal |
| 2.1.6 | Development of recommendations on the carrying out of interlaboratory comparison testing among laboratories that perform testing of substances, materials, objects of the environment (content and physical and chemical properties) | 2009 – 2009 | TC 1.8 | Within Project 211/RU/06 work has been done on carrying out ICT of impurities in vodka |
| 2.1.7 | Updating and implementation of the Programme of Comparisons of Measurement Standards of COOMET NMIs | 2008 – 2010 | JCMS, TC 1.1 – TC 1.12 | COOMET Programme of Comparisons was annually formed and approved by the COOMET President |
| 2.1.8 | Introduction of the electronic version of COOMET Calibration Certificate form | 2008 – 2009 | JCMS, TC 1.1 – TC 1.12 | Within Project 301/UA/04. Completed |
| 2.1.9 | Organisation of the scientific and practical workshop “Results and prospects of the implementation of the CIPM MRA” | 2009 | COOMET President, COOMET Vice-Presidents | The Workshop on the 10th Anniversary of the CIPM MRA: Results and Prospects of Cooperation was held on 22 September 2009 in Kazan, Russia |
| 2.1.10 | Continuation of the arrangements on joining the interested countries to ATA-CARNET system | 2008 – 2010 | Committee Members from interested countries | The following countries are members of ATA-CARNET: Belarus, Bulgaria, Germany, Lithuania, Moldova, Romania, Russia, Slovakia, Ukraine |
| 2.1.11 | Arrangements on the realisation of the CIS Agreement on Tax Free Policy of 1995 (with amendments) | On ratification | Committee Members from interested countries, JCMS | In association with NSCMetr of EASC |
| 2.1.12 | Holding of workshops on urgent issues of metrology in different subject fields of cooperation (along with TC meetings) | 2008-2010 | TC 1.1 – TC 1.12, TC 4 | 1. Support in Developing the Basic Metrological Infrastructure of COOMET Member Countries, 17–19 June 2008, Kharkov, Ukaine. 2. Preparing the Metrology Institutes of the Region to their Participation in the CIPM MRA, 1–3 December 2008, Astana, Kazakhstan. 3. Calibration. Verification. Traceability, 14–16 July 2009, Yerevan, Armenia. 4. Implementation of Quality Management Systems in NMIs According to ISO/IEC 17025, 14–15 October 2009, Tbilisi, Georgia. 5. Training Workshop for COOMET Auditors Carrying Out QMS Peer Reviews in NMIs according to ISO/IEC 17025, 1–3 December 2009, Chisinau, Moldova. 6. Evaluation of РТВ-CООМЕТ Project and Planning of the Second Phase, 1 July 2010, Kharkov, Ukraine. 7. Effective Presentation and Intercultural Awareness, 28–30 September 2010, Minsk, Belarus. 8. Training Workshop on Mass Measurement Uncertainty, 5–6 October 2010, Tbilisi, Georgia |
| 2.1.13 | Carrying out of activity in association with EASC on studying the problems of the introduction of measurement uncertainty | 2008 –2010 | TC 1.1 – TC 1.12, TC 2 | RMG 93-2009 “SSM. Evaluation of metrological characteristics of CRM” developed and approved at the 36th meeting of EASC. COOMET Recommendation “Use of the Terms “Measurement Error” and “Measurement Uncertainty”. General Principles” will be discussed at the 21st meeting of COOMET Committee. The Recommendation was considered at the meetings of COOMET TC 1.1 and EASC STC for Uncertainty |
| 2.1.14 | In-field implementation of COOMET Recommendation R/GM/14:2006 on the evaluation of the data of regional key comparisons | 2008 – 2010 | TC 1.1 – TC 1.12 | The Recommendation was approved |
| 2.1.15 | Development and in-field implementation of recommendations for the evaluation of the data of supplementary comparisons with the view of confirming CMC | 2008 –2010 | TC 1.1 – TC 1.12 | At the 18th meeting of COOMET Committee CООМЕТ Recommendation R/GM/19:2008 “Guide to Evaluation of Data of COOMET Supplementary Comparisons” |
| 2.1.16 | Participation in the regular international workshop “Mathematical, statistical and computer support of measurement quality” organized by VNIIM named after D.I. Mendeleev | 2009 | Committee Members from interested countries, JCMS, TC 4 | The International Workshop was held on 30 June – 2 July 2009 in Saint-Petersburg, Russia. The number of participants was 51 from 10 countries (Azerbaijan, Belarus, Bulgaria, Germany, Italy, Moldova, Russia, Uzbekistan, Ukraine, Chili). 36 reports were made |
| 2.2 | In the field of legal metrology |  |  |  |
| 2.2.1 | Development and realisation of the Working Programme in the field of legal metrology |  |  |  |
|  | - Development | 2008 | TC 2 | Completed |
|  | - Realisation | 2008 – 2010 | TC 2 |  |
| 2.2.2 | Analysis of cooperation projects proposed by international and regional organisations on legal metrology and formulation of suggestions on joint work on these projects | 2008 – 2010 | TC 2, SC 2.1 |  |
| 2.2.3 | Development of a sample programme for testing software for measuring instruments | 2008 – 2009 | TC 2, SC 2.2 | In progress |
| 2.2.4 | Development of a programme of generating “reference” data arrays for the purpose of testing software for measuring instruments | 2008 – 2009 | TC 2, SC 2.2 | In progress |
| 2.2.5 | Translation and preparation for publication of ISO/IEC Guide 99:2007 “International vocabulary of metrology – Basic and general concepts and associated terms (VIM)” | 2008 – 2009 | TC 2, SC 2.3 | Translation into Russian was made by VNIIM, Saint-Petersburg, Russia, BelGIM, Minsk, Belarus, and TC 1.1 members. Published in 2009, Saint-Petersburg, NPO “Professional” |
| 2.2.6 | Development of recommendations concerning the carrying out of comparisons between calibration laboratories for the purpose of evaluating their competence | 2008 – 2010 | TC 2, SC 2.4 |  |
| 2.3 | In the field of QMS |  |  |  |
| 2.3.1 | Development and realisation of the Collaboration Programme within COOMET Quality Forum |  |  |  |
|  | - Development | 2008 | TC 3.1 |  |
|  | - Realisation | 2008 – 2010 | Quality Forum |  |
| 2.3.2 | Preparation and holding of presentations of QMS of the NMIs of Armenia, Azerbaijan, Georgia, Kazakhstan, Kyrgyzstan, Uzbekistan at COOMET Quality Forum | 2008 | Committee Members from Armenia, Azerbaijan, Georgia, Kazakhstan, Kyrgyzstan, Uzbekistan at the Quality Forum, TC 3.1 | The presentation of KazInMetr was carried out in April 2007 during the 9th meeting of the Quality Forum. The peer review of KazInMetr’s QMS was held in November 2009. The Recognition Certificate was received in October 2010 |
| 2.3.3 | Carrying out of external reviews of QMS of GP “Ivano-Frankovskstandartmetrologia” (Ukraine) and NISM (Moldova) | 2008 According to an individual schedule | Quality Forum, TC 3.1, Committee Members | The peer review of the QMS of GP “Ivano-Frankovskstandartmetrologia” (Ukraine) was carried out in February 2008. The Recognition Certificate was received in April 2008. A training peer review of INSM (Moldova) was carried out in December 2009 |
| 2.3.4 | Consideration of the effectiveness of QMS of NMIs of COOMET Member Countries at COOMET Quality Forum for the purpose of confirming QMS recognition. | According to an individual schedule | Quality Forum, TC 3.1 | At the meetings of COOMET QF oral and written presentation of the following COOMET NMIs were considered in order to confirm the QMS recognition and give an access to QMS peer reviews: VNIIM, VNIIMS, VNIIOFI, VNIIFTRI – 2009, BelGIM, NSC “IM”, Ukrmetrteststandart – 2010. Repeated QMS peer reviews (after a 5-year period) of VNIIM, VNIIMS, VNIIOFI, VNIIFTRI (Russia) were held in October 2010. Recognition Certificates were issued in October 2010 |
| 2.3.5 | Submission of the COOMET Recommendation “Order and procedure for evaluating the quality management system of an NMI” for approval at the 18th COOMET Committee Meeting | 2008 | TC 3.1 | The COOMET Recommendation R/AQ/13:2010 was considered at the 10th, 11th, 12th meetings of COOMET QF; it was approved together with the revised Recommendation R/AQ/9:2010 at the 20th meeting of COOMET Committee |
| 2.3.6 | Introduction of ISO/IEC 17025:2005 and ISO Guide 34:2000 into the practice of COOMET Member Countries for activities carried out on national measurement standards | 2008 – 2010 | TC 3.1 | According to an individual plan |
| 2.3.7 | Updating of the database of auditors and technical experts of COOMET (from each COOMET Member Country that signed the CIPM MRA) | 2008 | Quality Forum, TC 3.1 | In progress |
| 2.3.8 | Arrangement of training courses for auditors and technical experts of COOMET | 2008 – 2010 | Quality Forum, TC 3.1 | A training workshop for COOMET auditors was held on 1–3 December 2009 at INSM, Chisinau, Moldova |
| 2.4. | Activity in the field of personnel training and information dissemination |  |  |  |
| 2.4.1 | Development and realisation of the Programme of Cooperation in the field of information and training |  |  |  |
|  | - Development | 2008 | TC 4 | Programme for 2009–2011 was developed and approved |
|  | - Realisation | 2008 – 2010 | TC 4 |  |
| 2.4.2 | Updating and publication of COOMET Directory | 2008 – 2010 (when necessary) | COOMET Secretariat | The Directory was published annually in the electronic form It was published in paper in 2008, 2009. |
| 2.4.3 | Modernization of the structure of the COOMET Website | 2008 – 2010 | Website Developer, COOMET Secretariat, WG on the Project | COOMET Project 478/UA-a/09 “Creation of a Working COOMET Web-Portal”. www.coomet.net was developed and launched in 2010 |
| 2.4.4 | Renewal of information posted on the COOMET Website | 2008 – 2010 (when necessary) | COOMET Secretariat, Website Developer | Taking Project 251/BY/01 into consideration |
| 2.4.5 | Working out and publication of at least three regional editions of COOMET (reports, research, annotations) per year in the area of metrology for the purpose of attracting the attention of political and economic societies of COOMET Member Countries | 2009 – 2010 | SC 4.2 COOMET Secretariat | In 2010 the annual reports of CSB were published as separate brochure. A flyer on COOMET activities in developing basic metrological infrastructures in Cebtral Asian and Caucasian countries was issued in 2009 |
| 2.4.6 | Development of training exchange programmes for experts within COOMET | 2008 – 2010 | SC 4.3 | Information is being compiled for developing the programme within COOMET Project 510/KZ/10 |
| 2.4.7 | Holding of a contest of scientific papers among young metrologists of COOMET Member Countries | once in 2 years (2009) | Contest Commission under COOMET President’s Council, TC 4 | III International Competition for Young Metrologists of COOMET Member Countries was held in April 2009 in Minsk, Belarus, COOMET Project 453/BY/09 |
| 2.4.8 | Establishment of Subcommittee 4.4 “Support for developing countries in the improvement of national metrology services” within TC 4 and elaboration of the fields of its activity | 2008 – 2009 | TC 4, SC 4.4 | SC 4.5 “Support in Developing the Metrological Infrastructure of COOMET Member Countries” was established in May 2008 |
| 2.4.9 | Determination of nominees for the distinguished title “Honorary metrologist of COOMET” and organisation of awarding | 2008 – 2010 | COOMET President, President’s Council, COOMET Committee | The distinguished title was given to 9 metrolgoists in 2008; 5 metrologists in 2009; 4 metrologists in 2010 |
| # 3 Collaboration with international, regional and national metrology organisations |  |  |  |  |
| 3.1 | Arrangement on the popularization of COOMET activities at the national and international levels | On continuous basis | COOMET President, COOMET Committee Members, COOMET Secretariat | Within an individual plan of actions |
| 3.2 | Maintenance of contacts with international and regional metrology organisations. Information exchange | On continuous basis | COOMET President, COOMET Secretariat | Representatives of international and regional metrology organizations participate in the meetings of COOMET Committee. COOMET Secretariat informs RMOs of the events conducted |
| 3.3 | Maintenance of contacts and participation in the events organised by regional organisations (EURAMET, APMP, SADCMET, SIM) | 2008 – 2010 | COOMET President, COOMET Committee Members, COOMET Secretariat | Completed for EURAMET, APMP, AFRIMETS (former SADCMET) |
| 3.4 | Collaboration with CIPM, BIPM, Consultative Committees for different kinds of measurement | On continuous basis | Vice-President responsible for coordination of COOMET activities in the field of measurement standards and interaction with CIPM and BIPM, JCMS Chairperson | The work is performed on continuous basis. COOMET representatives participated in the meetings of Consultative Committees |
| 3.5 | Encouragement of participation of COOMET Representatives in the work of JCRB | According to the JCRB schedule | Vice-President responsible for coordination of COOMET activities in the field of measurement standards and interaction with CIPM and BIPM (COOMET Representative to JCRB) | COOMET representatives participated in all meetings of JCRB and informed the participants of the meetings of the activity on the CIPM MRA implementation |
| 3.6 | Maintenance of contacts with international and regional organisations on legal metrology (OIML, WELMEC, APLMF, SADCMEL, etc.) | On continuous basis | COOMET President, Vice-President responsible for coordination of cooperation in the field of legal metrology, TC 2 Chairperson | COOMET representatives participated in the 13th OIML Congress, 43rd–45th meetings of CIML, all meetings of the round Table of Regional Legal Metrology Organizations, meetings of WELMEC |
| 3.7 | Maintenance of contacts with international and regional organisations on accreditation (ILAC, IAF, EA, APLAC) | On continuous basis | Vice-President responsible for coordination of COOMET activities in the field of quality management systems and accreditation | Accreditation was excluded from COOMET activity areas |
| 3.8 | Maintenance of contacts with EASC NSCMetr of the CIS | On continuous basis | COOMET President COOMET Secretariat | COOMET representatives participated in the meetings of EASC and STCMetr |
| 3.9 | Establishment and maintenance of contacts with national metrology organisations interested in the cooperation with COOMET | On continuous basis | COOMET President COOMET Secretariat | Contacts were established with NCSLI; a MoU was signed in 2010 |