|  | СООМЕТ-21/05.1 (2) |
| --- | --- |

DRAFT

COOMET DEVELOPMENT PROGRAMME FOR 2011–2013

| No. | Name of event | Terms | Executors | Remarks |
| --- | --- | --- | --- | --- |
| 1 Improvement of COOMET infrastructure and activity arrangement |  |  |  |  |
| 1.1 | Evaluation of the level of realisation of COOMET Conception of Cooperation | 2011–2013 | Participants of cooperation in COOMET |  |
| 1.2 | Organisation of work on the implementation of the Decisions of the 24th CGPM in connection with the possible redefinition of the main SI units | 2012–2013 | COOMET President, COOMET Committee Members |  |
| 1.3 | Development of conception of the main scientific research works in the field of metrology in COOMET member-countries | 2011–2012 | President’s Council, COOMET Secretariat | Within the Project 492/DE/10 |
| 1.4 | Realisation of the Protocol of Cooperation between COOMET and EASC in the area of metrology | 2011–2013 | COOMET President, COOMET Committee Members |  |
| 1.5 | Notification about changes in COOMET Structural Bodies (TCs and SCs) | When necessary | Chairpersons of CSB, COOMET Secretariat |  |
| 2 Activity in some fields of cooperation |  |  |  |  |
| 2.1 | In the area of measurement standards |  |  |  |
| 2.1.1 | Arrangements on the signing of the Agreement on Mutual Recognition (CIPM MRA) by Azerbaijan, Armenia, Kyrgyzstan, Tajikistan and Uzbekistan | 2011–2013 | Committee Members from Azerbaijan, Armenia, Kyrgyzstan, Tajikistan and Uzbekistan |  |
| 2.1.2 | Activity on the realization of the CIPM MRA | 2011–2013 | COOMET Representative in JCRB, Joint Committee on Measurement Standards (JCMS) | COOMET responsible representatives participate in the meetings of JCRB |
| 2.1.3 | Updating and implementation of the Programme of Comparisons of Measurement Standards of COOMET NMIs | 2011–2013 | JCMS, TC 1.2 – TC 1.12 |  |
| 2.1.4 | Development and on-line maintenance at COOMET web-portal of the Programme of Comparisons of Measurement Standards NMIs of COOMET member-countries | 2011–2012 | JCMS, COOMET Secretariat | Updating of the COOMET Recommendation R/GM/12:2007 “Maintenance rules of the Programme of Comparisons of COOMET” |
| 2.1.5 | Development, updating and implementation of the Programme of Mutual Development of Reference Materials within COOMET | On continuous basis within Project 186/RU/99 | ТC 1.12 |  |
| 2.1.6 | Preparation of СМС data, organisation of their consideration in COOMET and submission for an interregional review | 2011–2013 | Committee Members from Belarus, Georgia, Kazakhstan, Moldova, Russia, Ukraine, JCMS Committee Members from Azerbaijan, Armenia, Kyrgyzstan, Tajikistan after the signing of the CIPM MRA | The work is performed as CMCs appear |
| 2.1.7 | Development of the pages of on-line expertise of CMC-entries on kinds of measurements at COOMET web-portal | 2011–2012 | JCMS, COOMET Secretariat | Within the Project 478/UA-a/09 |
| 2.1.8 | Organization of the workshops on practical preparation for the comparisons and submission of CMC-data | 2011–2013 | ТC 1.6, ТC1.9, ТC 1.10, ТC4 |  |
| 2.1.9 | Holding of workshops on urgent issues of metrology in different subject fields of cooperation | 2011 | ТC 1.12 | III All-Russian scientific and technical conference with international participation “Reference materials in measurements and technologies”, 12-17 September 2011, Yekaterinburg, Russia |
| 2.2 | In the field of legal metrology |  |  |  |
| 2.2.1 | Development and realisation of the Working Programme in the field of legal metrology for 2011 – 2013 |  |  |  |
|  | - Development | 2011 | Chairperson of TC 2 |  |
|  | - Realisation | 2011–2013 | TC 2 Members |  |
| 2.2.2 | Analysis of possible fields of cooperation with OIML and regional organizations on legal metrology. formulation of suggestions on joint work with them | 2011–2012 | Chairperson of ТC 2 |  |
| 2.2.3 | Development of a sample Programme for testing software for measuring instruments | 2011–2012 | ТC 2, SC 2.2 |  |
| 2.2.4 | Development of a programme of generating “reference” data arrays for the purpose of testing software for measuring instruments | 2011–2012 | ТC 2, SC 2.2 |  |
| 2.2.5 | Realization of the Project “Procedure of rating the technical devices to measuring instruments ” | 2011–2013 | TC 2, SC 2.2 |  |
| 2.2.6 | Development of Recommendations on conducting comparisons between verification laboratories with the aim of their competence evaluation | 2011–2012 | ТC 2, SC 2.4 |  |
| 2.2.7 | Creation of data base of normative documents in the field of metrology of COOMET member-countries | 2011–2013 | TC 2 Members |  |
| 2.3 | In the field of QMS |  |  |  |
| 2.3.1 | Development and realisation of the Collaboration Programme within COOMET Quality Forum for 2008 – 2010 |  |  |  |
|  | - Development | 2011 | Chairperson of TC 3.1 |  |
|  | - Realisation | 2011–2013 | ТC 3.1, Quality Forum |  |
| 2.3.2 | Preparation and holding of oral presentations of Quality Management Systems of NMIs, which are not still the CIPM MRA signatories (Azerbaijan, Armenia, Kyrgyzstan, Tajikistan and Uzbekistan) | 2011–2013 | Committee Members from Azerbaijan, Armenia, Kyrgyzstan, Tajikistan and Uzbekistan at the Quality Forum, TC 3.1 |  |
| 2.3.3 | Carrying out of written and oral presentations of QMS NMIs: UNIIM (Russia), SNIIM (Russia), VNIIR (Russia), DP NDI “Systema” (Ukraine), NISM (Moldova) | 2011 | Quality Forum, ТC 3.1, Committee Members |  |
| 2.3.4 | Carrying out of second circle of external reviews of QMS of UNIIM (Russia), SNIIM (Russia), DP NDI “Systema” (Ukraine) | 2012 | Quality Forum, ТC 3.1, Committee Members |  |
| 2.3.5 | Carrying out of external reviews of QMS of VNIIR (Russia), NISM (Moldova), Institute of metrology in GEOSTM (Georgia) | According to an individual schedule | Quality Forum, ТC 3.1, Committee Members |  |
| 2.3.6 | Arrangement of training courses for auditors and technical experts of COOMET | 2012–2013 | Quality Forum, ТC 3.1, ТC 4 |  |
| 2.4. | Activity in the field of personnel training and information dissemination |  |  |  |
| 2.4.1 | Development and realisation of the Programme of Cooperation in the field of information and training for 2012–2013 |  |  |  |
|  | - Development | 2011 | Chairperson of TC 4 |  |
|  | - Realisation | 2012–2013 | TC 4 Members |  |
| 2.4.2 | Updating and publication of COOMET Directory | 2011–2013 | COOMET Secretariat |  |
| 2.4.4 | Renewal of information posted on the web-portal and COOMET web-site | 2011–2013 | COOMET Secretariat, On-line editors of countries and TCs, web-site Administrator | Taking Project 500/UA/10 into consideration |
| 2.4.5 | Working out and publication of at least three regional editions of COOMET (reports, research, annotations) per year in the area of metrology for the purpose of attracting the attention of political and economic societies of COOMET Member Countries | 2011–2013 | SC 4.2, COOMET Secretariat |  |
| 2.4.6 | Development of the Programme of trainings for specialists including young metrologists within COOMET | 2011–2013 | SC 4.3 | Within the Project 510/KZ/10 |
| 2.4.7 | Holding of a contest of scientific papers among young metrologists of COOMET Member Countries | once in 2 years (2011, 2013) | Contest Commission under COOMET President’s Council, TC 4 |  |
| 2.4.8 | Support in improvement of national metrology services of COOMET Member Countries | 2011–2013 | ТC 4, SC 4.5 | Within the COOMET-PTB Project “ Support in Developing the Metrological Infrastructure of COOMET Member Countries” |
| 2.4.9 | Determination of nominees for the distinguished title “Honorary metrologist of COOMET” and organisation of awarding | 2011–2013 | COOMET President, President’s Council, COOMET Committee |  |
| # 3 Collaboration with international, regional and national metrology organisations |  |  |  |  |
| 3.1 | Arrangement on the popularization of COOMET activities at the national and international levels | 2011–2013 | COOMET President, COOMET Committee Members, COOMET Secretariat |  |
| 3.2 | Maintenance of contacts with international and regional metrology organisations. Information exchange | 2011–2013 | COOMET President, COOMET Committee Members, COOMET Secretariat |  |
| 3.3 | Maintenance of contacts and participation in the events organised by regional organisations (EURAMET, APMP, SADCMET, SIM) | 2011–2013 | COOMET President, President’s Council, COOMET Secretariat |  |
| 3.4 | Collaboration with CIPM, BIPM, Consultative Committees for different kinds of measurement | 2011–2013 | COOMET-President, Vice-President responsible for coordination of COOMET activities in the field of measurement standards and interaction with CIPM and BIPM, JCMS Chairperson, COOMET Secretariat |  |
| 3.5 | Encouragement of participation of COOMET Representatives in the work of JCRB | According to the JCRB schedule | COOMET-President, Vice-President responsible for coordination of COOMET activities in the field of measurement standards and interaction with CIPM and BIPM, JCMS Chairperson, COOMET Secretariat |  |
| 3.6 | Maintenance of contacts with international and regional organisations on legal metrology (OIML, WELMEC, APLMF, SADCMEL, etc.) | 2011–2013 | COOMET President, Vice-President responsible for coordination of cooperation in the field of legal metrology, Chairperson of TC 2, COOMET Secretariat |  |
| 3.8 | Maintenance of contacts with EASC NSC Metr of the CIS | 2011–2013 | COOMET President’s Council, COOMET Secretariat |  |
| 3.9 | Maintenance of contacts and participation in the events of NCSLI | 2011–2013 гг. | COOMET President’s Council, COOMET Secretariat |  |